MITTIVA

Practical AI for Chennai SMBs

30 / 60 / 90

Brand & Growth Strategy

Channels  ·  LinkedIn / Instagram / Facebook

Geography  ·  Chennai & native India

Prepared for  ·  Vidyut & Sanskar Poddar

Date  ·  May 2026  ·  v1.0

# 1. Executive Summary

A bootstrap-friendly, 90-day plan to take Mittiva from cold start to its first proof of pull — measurable inbound, a foundation of case studies, and a small but real MRR engine.

### The mission, in one line

“Make Mittiva the default name a Chennai family-business successor types into Google when they finally decide to drag the shop into 2026.”   — The 90-day mission

### What "good" looks like at Day 90

- 5,000+ followers combined across LinkedIn, Instagram and Facebook.

- 200+ inbound DMs / inquiries from ICP-fit founders and successors.

- 25–30 discovery calls held.

- 7–10 paying customers signed.

- ₹38K–₹55K MRR run-rate by end of Day 90.

- 3 published, polished case studies — the Hour Back series volume one.

- Brand recognition inside 2–3 Chennai family-business WhatsApp / Facebook groups.

### Budget envelope

Bootstrap range ₹10,000–₹25,000 per month. Most of the lift is organic + AI-assisted content; paid spend is layered in only after Day 30 when there is creative worth boosting.

# 2. Positioning Recap

Restating what is already on the website so every post, ad, and DM can ladder up to it.

### What Mittiva is

An AI studio built by two brothers in Chennai for the businesses that built our neighbourhoods. Eight productized services — Voice AI, Conversation AI, Social Media Automations, AI Changing Room, Website Development, Email Design Kit, Automations, and CRM. Scoped tightly. Priced honestly. Shipped in weeks.

### What Mittiva is not

- Not a consultancy in suits selling decks.

- Not a Silicon Valley import telling Chennai how to work.

- Not a freelance shop — we own the system end to end.

- Not for venture-scale tech companies — we are for the tailor, the tutor, the salon.

### Brand voice

- Editorial — stacked headlines, set type, magazine-grade restraint. (Already lives in the website.)

- Neighbourhood-rooted — specific street names, specific shop names, specific Tamil/English bilingualism.

- Quietly confident — we don’t shout. We show the hour we gave back.

- Plain-spoken — if Sanskar’s amma can’t parse the sentence, we rewrite it.

### Core promise (the line every campaign tests against)

“AI shouldn’t only belong to big companies.”   — mittiva.io

# 3. The Ideal Customer

Mittiva sells to the small business, but it markets to the successor — the person who quietly drives the buying decision because they’re embarrassed by the WhatsApp inbox their family runs the shop on.

### Primary ICP — "The Successor"

| Who | Son or daughter, 22–32, joined the family business in the last 0–3 years. Recent grad, returning MBA, or burned out from a corporate job. Often the only person in the building under 40 who has a LinkedIn. |
| --- | --- |
| Family business size | ₹50L–₹5Cr annual revenue. 3–20 employees. F&B, retail, boutique, salon, clinic, tuition centre, jewellery, textiles, services. Traditional but profitable. |
| What stings | Father runs everything in his head. Mother takes orders on WhatsApp at 11pm. Calls get missed. Ledgers are paper. “CRM” is a notebook. The competition opened an Instagram and people are noticing. |
| What they want | To prove they belong. To leave a mark. To bring the business into 2026 without disrespecting the way the previous generation built it. They want a small, undeniable win they can show at the dinner table. |
| Decision power | Influencer-plus. They can sign off ₹10K–₹50K on their own. Bigger spends need a five-minute pitch to dad. |
| Where they live online | LinkedIn (building their professional identity), Instagram (inspiration and reels), WhatsApp (everything else). They lurk in Chennai entrepreneur Facebook groups but post on LinkedIn. |
| Tone that lands | Editorial, specific, founder-led. They scroll past stock-photo agency posts in 0.4 seconds. They stop on a 90-second video of a real Mylapore shopkeeper getting an hour back. |

### Secondary audience — "The Patriarch / Matriarch"

We don’t target them directly, but they bless the deal. Facebook is the channel that reaches them. Trust signals — Chennai, family-run, in-person handshake, neighbours who already use us — do the work.

### Who we are NOT for (yet)

- Pre-revenue startups with no customers.

- Enterprise IT departments looking for an RFP-driven vendor.

- Marketing agencies looking for a white-label partner.

# 4. Channel Strategy

Three platforms, three jobs. Don’t expect the same content to do the same work on each.

| Channel | Job to be done | Audience hit | Primary format |
| --- | --- | --- | --- |
| LinkedIn | Authority + inbound. Where the Successor decides we are credible enough to message. | The Successor directly. Plus their cousins, friends, and other family-business operators. | Founder-led long-form text, customer carousels, weekly Workshop demos, occasional live. |
| Instagram | Transformation theatre. Show the AI in action and the hour it gave back. | The Successor in their off-hours. Their cousins. Local Chennai feeds. | Reels (3×/wk), stories (daily), 1 carousel/wk. Tamil + English captions. |
| Facebook | Trust + local proof. Where the Patriarch quietly checks if we’re real. | Parents. Aunts, uncles, neighbours. Chennai SMB / family-business groups. | Repurposed IG reels + community presence in Chennai entrepreneur FB groups. |

### Where the work goes first

LinkedIn is the primary inbound engine. Both founder profiles (Vidyut + Sanskar) should be treated as cornerstone media. The Mittiva company page is a mirror, not the source. Most successful Indian agency-style brands at this stage get 60–80% of their inbound from founder profiles, not company pages — we will plan accordingly.

# 5. Content Pillars

Five recurring series that each post can be sorted into. Pillars buy us repeatability and brand memory.

### 01 · The Workshop

Behind the build. Short, specific demos of one Mittiva product doing one job. The voice agent answering a Tamil call. The WhatsApp bot taking an order. The CRM kanban moving a card from Warm to Won. Usually 45–90 second reels, repurposed as LinkedIn videos and FB posts.

### 02 · The Hour Back

The customer transformation series. Before → after with a number on it. "Lakshmi & Daughters used to write order pickups on paper. Now: 14 hours / week back." This pillar is where the case studies live and where conversion happens.

### 03 · Two Brothers’ Notes

Founder-led POVs. Vidyut on systems, architecture, what builds break. Sanskar on customers, brand, story. Long-form LinkedIn posts. Sometimes contrarian — "AI agencies are mostly selling decks. We don’t do decks." This pillar is what makes the brand stick.

### 04 · Field Notes

Sightings of broken SMB processes around Chennai. "Saw a sari shop in T. Nagar today turning away customers because their landline was busy." Each Field Note ties back to a service we offer without being preachy. Format: photo carousel or a single moody portrait shot of the street.

### 05 · AI, Demystified

Plain-language explainers for non-technical founders. "What is a voice agent and what isn’t it?" "Three myths about AI for small businesses." Bilingual (English + Tamil) where it makes sense. Carries the brand promise of "we explain it so your accountant gets it."

### Posting cadence by pillar (per week)

| The Workshop | 1 reel (cross-posted IG/FB), 1 LinkedIn video |
| --- | --- |
| The Hour Back | 1 case-study post (carousel on LinkedIn + IG, photo set on FB) |
| Two Brothers’ Notes | 3–4 long-form posts (LinkedIn-first, Vidyut + Sanskar split) |
| Field Notes | 1–2 IG carousels, 1 FB share |
| AI, Demystified | 1 LinkedIn carousel, 1 IG reel |

# 6. Days 1–30 · Foundation

“Plant the brand. Get one paying customer. Make week-one content that you’d be proud to pin a year from now.”   — Phase one mission

### Week 1 · Stand it up

- Polish all three profiles — same handle (@mittiva.io / Mittiva), same editorial header image, the manifesto pinned at top.

- Audit Vidyut + Sanskar personal LinkedIns: banner, headline ("Co-founder, Mittiva · Practical AI for Chennai SMBs"), featured section with website link.

- Tools: Canva Pro (₹500/mo), Metricool free tier, WhatsApp Business, GA4 already on the site, Notion or Sheets content calendar.

- Build a 50-name "warm 50" list: cousins, classmates, anyone you already know who works in a family business. They are your launch audience.

- Batch the first 14 days of content using AI (Claude + ChatGPT for drafts; you edit). Aim for a 3-hour writing block, not 30 minutes a day.

### Weeks 2–3 · Launch

- Series launch: "Two Brothers, One Workshop" — a 3-part founder video, one per week. Shot on a phone, edited in CapCut. Voiceover in English with Tamil sub-titles.

- Post the website manifesto as a LinkedIn carousel and an IG carousel.

- Drop the first Workshop demo: voice agent picking up a call in Tamil. 60 seconds. End with "this could be your phone, by Friday."

- Vidyut and Sanskar each ship 2 long-form LinkedIn posts in week 2 — differentiated POVs to avoid sounding like one voice.

- Outbound: 20 personalized DMs per week. Pattern: "Saw your shop on [street]. Noticed [specific thing]. Built something that fixes it — happy to show you in 15 min, no charge."

### Week 4 · First close

- Offer 2 free or 50%-off pilots in exchange for the right to document everything as a case study. Target: tailor, salon, tutoring centre, small clinic, or boutique.

- Capture before-state on camera. Time the manual process with a stopwatch. This footage is the Hour Back episode 1.

- Begin first paid acquisition test: ₹3,000 boost on the single best-performing organic post. Goal is learning, not leads.

### Phase one targets

| Followers (combined) | 300–500 |
| --- | --- |
| Inbound DMs / inquiries | 25–40 |
| Discovery calls booked | 5–8 |
| Paying or pilot customers | 1–2 |
| Revenue (collected) | ₹10,000–₹15,500 |
| Spend | ₹10,000–₹12,000 |

# 7. Days 31–60 · Amplification

“Take what is working organically and put a small amount of fuel on it. Land case study one. Move customer count from 1 to 4.”   — Phase two mission

### Weeks 5–6 · First proof

- Publish Case Study #1 — The Hour Back, episode one. A 90-second hero video + a long-form LinkedIn carousel + an IG reel cutdown.

- Founder LinkedIn live: "What we built for [customer] in 7 days." 25 minutes, low production. Repurpose the recording for 4–5 short clips.

- Launch lead magnet: "AI Readiness Checklist for Family Businesses." A 1-page PDF. Free in exchange for an email. Hosted on the existing site — add a /checklist landing page.

- Begin light paid: ₹3–5K boosting the case study video to a Chennai SMB lookalike. Track DMs, not vanity metrics.

### Weeks 7–8 · Distribution

- Customer #2 and #3 — paid, no longer pilots. Use the case study as the closer in every discovery call.

- WhatsApp broadcast list: every inbound DM gets added (with consent). Send one fortnightly broadcast — a Field Note or a Workshop clip.

- Outbound scales to 30 DMs/week, split between Vidyut and Sanskar.

- Pitch 5 Tamil entrepreneurship podcasts and YouTube channels (Storiyoh, Vibgyor, Madras Inc, etc.). Aim for one booking by Day 60.

- Step paid up to ₹8–12K — split between the case study creative and a "Mittiva Origin" video. Test 2 ad sets, kill the loser by week 8.

### Phase two targets (cumulative)

| Followers (combined) | 1,200–1,500 |
| --- | --- |
| Inbound DMs / inquiries | 70–100 total |
| Discovery calls booked | 12–15 total |
| Total customers | 3–4 |
| Revenue (cumulative through Day 60) | ₹45,000–₹60,000 |
| MRR end of Day 60 | ₹16,500–₹22,000 |
| Cumulative spend | ₹30,000–₹42,000 |

# 8. Days 61–90 · Conversion

“Move from "interesting" to "obvious." Three case studies, a referral motion, a productized audit, and paid acquisition that compounds.”   — Phase three mission

### Weeks 9–10 · Stack the proof

- Publish Case Studies #2 and #3. Each gets the full treatment: hero video, carousel, blog post on the Mittiva site, and FB share.

- Launch the referral motion: every existing customer who brings in a new one gets ₹2,000 off and one free service-month. Announce in WhatsApp broadcast first — customers should hear it before LinkedIn does.

- Lock in one founder appearance — podcast or local SMB event. Aim for The Hindu MetroPlus listing or a Chennai entrepreneur meet.

### Weeks 11–12 · Productize and scale

- Productize the lead magnet into a paid "AI Audit" — ₹999, refundable on signup. Two outcomes: revenue from people who never sign, or full credit for people who do. Either way, you de-risk the funnel.

- Scale Meta ads to ₹12–15K/month: 3 ad sets running — case study, founder POV, AI Audit lead magnet. Retargeting layer on website visitors. Lookalike off paying customers (now you have a seed audience).

- Email nurture sequence — 5 emails over 14 days, auto-deployed when someone downloads the checklist or books a call. Built in Brevo (free tier covers it).

### Week 13 · Quarterly review

- Interview every existing customer. Capture 3–5 video testimonials (60 seconds each). These power Q2.

- Pull the data: which posts drove discovery calls, which ads converted, which channels under- or over-indexed. Build the Q2 content calendar against what worked.

- Decide retention motion for paying customers — monthly check-in, quarterly business review, or product-led notifications.

### Phase three targets (cumulative, Day 90)

| Followers (combined) | 3,500–5,000 |
| --- | --- |
| Inbound DMs / inquiries | 200–250 total |
| Discovery calls booked | 25–30 total |
| Total customers | 7–10 |
| Revenue (cumulative through Day 90) | ₹1,25,000–₹1,65,000 |
| MRR end of Day 90 | ₹38,500–₹55,000 |
| Cumulative spend (90 days) | ₹50,000–₹70,000 |
| Case studies published | 3 |
| Founder appearances | 1–2 |

# 9. Revenue Goals

Built off your unit economics: ₹10,000 project + ₹4,000–₹7,000 recurring (we use ₹5,500 as the blended average MRR per customer).

### Conservative scenario (the plan we commit to)

| Month | New customers | Total paying | Revenue collected | End-of-month MRR |
| --- | --- | --- | --- | --- |
| M1 | 1 | 1 | ₹15,500 | ₹5,500 |
| M2 | 2 | 3 | ₹36,500 | ₹16,500 |
| M3 | 4 | 7 | ₹78,500 | ₹38,500 |
| Total / End | 7 new | 7 active | ₹1,30,500 cumulative | ₹38,500 run-rate |

### Stretch scenario (what we aim for if Day-30 momentum is strong)

| Month | New customers | Total paying | Revenue collected | End-of-month MRR |
| --- | --- | --- | --- | --- |
| M1 | 2 | 2 | ₹31,000 | ₹11,000 |
| M2 | 3 | 5 | ₹57,500 | ₹27,500 |
| M3 | 5 | 10 | ₹1,05,000 | ₹55,000 |
| Total / End | 10 new | 10 active | ₹1,93,500 cumulative | ₹55,000 run-rate |

Note: revenue numbers assume ₹10K project fee is collected in the month of signup, and the first MRR cycle bills the month after. We round one new customer = +₹5,500 MRR.

# 10. Engagement Goals

Vanity metrics that actually correlate with pipeline at this stage. Don’t chase follower counts in isolation — the metric that pays the bills is "inbound DMs per week."

### LinkedIn (Vidyut + Sanskar combined)

| Month | Connections | Weekly impressions | Weekly profile views |
| --- | --- | --- | --- |
| M1 | 800 | 5,000 | 50 |
| M2 | 1,500 | 12,000 | 120 |
| M3 | 2,500 | 25,000 | 250 |

### Instagram (@mittiva.io)

| Month | Followers | Monthly reach | Engagement rate |
| --- | --- | --- | --- |
| M1 | 250 | 8,000 | 5% |
| M2 | 700 | 25,000 | 6% |
| M3 | 1,500 | 60,000 | 7% |

### Facebook (Mittiva page + Chennai groups)

| Month | Page followers | Monthly reach | Groups joined / active |
| --- | --- | --- | --- |
| M1 | 150 | 4,000 | 3 |
| M2 | 400 | 12,000 | 6 |
| M3 | 900 | 30,000 | 8 |

### Cross-channel pipeline targets

| Inbound DMs per week (Day 30) | 6–10 |
| --- | --- |
| Inbound DMs per week (Day 60) | 15–25 |
| Inbound DMs per week (Day 90) | 40–60 |
| DM → discovery call conversion | 15–20% |
| Discovery call → customer conversion | 25–35% (target by Day 90) |

# 11. Budget Breakdown

Designed against your bootstrap envelope of ₹10,000–₹25,000/month. Spend ramps as proof accumulates — we don’t put paid behind unproven creative.

### Month 1 · Foundation (target: ₹10,000–₹12,000)

| Line item | Cost | Note |
| --- | --- | --- |
| Canva Pro | ₹500 | Monthly; team plan for 2 if needed |
| Metricool (free) | ₹0 | Free tier covers IG/FB/LinkedIn scheduling |
| AI tools (Claude, ChatGPT, ElevenLabs) | ₹2,000 | Heavy lift on content drafting |
| Meta boost test (one post) | ₹3,000 | Learning spend, not lead spend |
| Stock B-roll (Storyblocks or Pexels) | ₹1,000 | Optional — Pexels covers most of it |
| Founder coffee meetings allowance | ₹2,000 | Cost of doing business in Chennai |
| Buffer / misc | ₹1,500 | Domain renewals, small tools |
| Total | ₹10,000 | Under-spends on purpose |

### Month 2 · Amplification (target: ₹18,000–₹22,000)

| Line item | Cost | Note |
| --- | --- | --- |
| Canva Pro | ₹500 |  |
| Metricool (paid analytics) | ₹1,500 | Worth it once posting cadence is steady |
| AI tools | ₹2,000 |  |
| Meta ads (2 ad sets) | ₹10,000 | Case study video + founder POV |
| Freelance video editor (1 case study) | ₹3,000 | Hire once, polish episode 1 |
| Founder + outreach allowance | ₹2,000 |  |
| Buffer / misc | ₹1,000 |  |
| Total | ₹20,000 |  |

### Month 3 · Conversion (target: ₹22,000–₹25,000)

| Line item | Cost | Note |
| --- | --- | --- |
| Canva Pro | ₹500 |  |
| Metricool | ₹1,500 |  |
| AI tools (incl. ElevenLabs Pro) | ₹2,500 | Bilingual demo content |
| Meta ads (3 ad sets + retargeting) | ₹13,000 | Scale the winners; lookalike off customers |
| Freelance video editor (2 case studies) | ₹3,500 |  |
| Brevo email (paid, optional) | ₹500 | Free tier works for first 2 months |
| Podcast/event booking allowance | ₹1,500 | Travel/recording costs |
| Buffer / misc | ₹1,000 |  |
| Total | ₹23,500 | Within ₹25K ceiling |

### 90-day spend vs. revenue at a glance

| Total 90-day spend (conservative) | ₹53,500 |
| --- | --- |
| Total 90-day revenue (conservative) | ₹1,30,500 |
| Net (cash, ignoring delivery cost) | +₹77,000 |
| MRR run-rate at Day 90 | ₹38,500 |
| Marketing CAC (blended) | ~₹7,650 per customer |
| Months to recoup CAC at ₹5.5K MRR | ~1.4 months |

# 12. Tools Stack (Bootstrap Edition)

Every tool justified, with the free path called out where it exists.

| Job | Tool | Cost | Why |
| --- | --- | --- | --- |
| Content drafts | Claude + ChatGPT | ₹1,500–2K/mo | LinkedIn long-form, IG captions, FB descriptions. Founders edit, never publish raw. |
| Design | Canva Pro | ₹500/mo | Carousels, story templates, branded color/font set. Reusable Mittiva templates. |
| Scheduling | Metricool | Free → ₹1.5K/mo from M2 | One queue for IG, FB and LinkedIn. Better hashtag suggestions than Buffer. |
| Video editing | CapCut | Free | Phone-first. All Workshop demos and Hour Back cutdowns. |
| Voice / audio demos | ElevenLabs | Free → ₹500 from M3 | Sample Tamil + English voice agent clips for demo reels. |
| Lead capture & CRM | Mittiva CRM | ₹0 (yours) | Eat your own dogfood. Every screenshot becomes a case for the product. |
| Email | Brevo | Free → ₹500 if list >300 | Nurture sequence + monthly broadcast. Free up to 300 contacts. |
| WhatsApp | WhatsApp Business | Free | Broadcast lists, quick replies, catalog. API upgrade only if M3 demands it. |
| Analytics | GA4 + platform native | Free | Already on mittiva.io. Set up conversion goals around contact-form fills. |

# 13. KPI Dashboard & Review Cadence

Track weekly, review monthly. Anything not on this list is decoration.

### Weekly metrics (pull every Monday morning)

- Inbound DMs / messages (the leading indicator of pipeline).

- Discovery calls booked.

- Posts published per channel.

- Top 3 posts by reach and by saves.

- Paid spend vs. plan.

### Monthly metrics (end of month review)

- Followers per channel (and delta vs. previous month).

- Total reach per channel.

- Profile views (LinkedIn) and saves (IG).

- New customers signed; total active customers.

- Revenue collected; MRR end-of-month.

- CAC blended (total spend / new customers).

- Net Promoter Score from existing customers (single question, sent monthly).

### Review rituals

- Monday standup (15 min, just brothers) — what shipped last week, what ships this week, who needs a nudge.

- End-of-month review (60 min) — KPI dashboard, top performers, what to kill, what to double.

- Quarterly customer interview (60 min per customer) — the source material for Q2 case studies and the brand promises you keep refining.

# 14. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Zero paying customers by Day 30 | Medium | Extend free pilot offer to 3 customers. Reach harder into the "warm 50" list. Reduce minimum scope to a single Workshop install. |
| Content fatigue / posting drops | High | Batch 4 weeks at a time. Use AI for 60% of first drafts. Build a 30-post "evergreen library" by end of M1. |
| Meta ad spend doesn’t convert | Medium | Cap M1 paid at ₹3K (a learning spend). Don’t scale until one ad set hits CPM under ₹250 and CPC under ₹6. |
| LinkedIn algorithm change tanks organic | Low-medium | Don’t put all chips on one platform. Maintain the WhatsApp broadcast as a direct-to-audience hedge. |
| Founder bandwidth dries up | High | Defend a 3-hour Sunday batch block. Outsource video editing from M2. Only Two Brothers’ Notes pillar requires raw founder voice. |
| A customer churns visibly / publicly | Low at this volume | Monthly check-in cadence catches dissatisfaction early. Pull case study if a customer goes quiet for 3 weeks. |

# 15. What I Need From You to Get Moving

A short list to finalize before Day 1. None of these block the strategy; they sharpen it.

- Three to five photos of you and Sanskar that match the editorial portrait style the website already uses. Founder profiles need them by Week 1.

- A confirmed "warm 50" list — cousins, classmates, anyone you already know who works in a family business. This is your launch audience.

- One vertical hypothesis: are we leading with boutiques, F&B, clinics, tuition centres, or staying horizontal? A narrow lead vertical compounds faster. (Recommendation: start with boutiques or tuition centres — high IG presence, clear ROI story.)

- Confirmation that the AI Changing Room demo is shootable inside Q1 — if yes, it becomes the hero Workshop reel for IG.

- 1–2 friendly contacts willing to be pilot customer for the first Hour Back case study.

- Approval to begin posting from the Vidyut + Sanskar personal LinkedIns as the primary inbound surface (not just the company page).

Strategy v1.0 — designed to be reviewed every 30 days and re-cut at Day 90.

Made in Chennai. For the businesses that built our neighbourhoods.